## Sheet1
Sl. No | System | Type | Description | Priority | Status | JIRA | Resource Name | Status | Star Date
1 | CRM | Bug | On clicking product -> External number button shows “ 404 errors” | 2-High | Open | http://jira04.switchlab.com/browse/URM-230 | Dharmaveeran | Yet to be start
|  |  | This error was occurs in other tab also (occurs occasional) |  |  | http://jira04.switchlab.com/browse/URM-265 | Dharmaveeran | Yet to be start
2 | CRM | Bug | The Product Amount is inconsistent between CRM and MyAccount. | 2-High | Open | http://jira04.switchlab.com/browse/UFM-458 | Dharmaveeran | In-Progress | 2014-06-05
MyAccount: Automated Operator cost is $10.00
CRM: Automated Operator is $15.00
3 | CRM | Bug | Bundle isn’t showing with their respective numbers | 2-High | Open
[6 empty] | http://jira04.switchlab.com/browse/URM-301 | Dharmaveeran | Yet to be start |  | D | J | J
4 | CRM | Bug | Even though the Item is provisioned and dispatched the Sim extensions are not displayed for Individual sim plans in Products sub tab of Order tab. See attached screen shots. | Critical | Open | http://jira04.switchlab.com/browse/URM-303 |  |  |  | D
5 | CRM | Bug | When trying to provision the mobile number, clicking on the provision button error message comes up but though the number gets provisioned | 2-High | Open | http://jira04.switchlab.com/browse/URM-304 | Dharmaveeran | Yet to be start
When trying to dispatch the mobile number, though a error message comes up while clicking on the submit button of Royal mail reference the number gets dispatched.
| CRM | Customer - Bug | Customer > product >mobile plans >select action >upgrade Action from CRM is not reflecting on MyAccount | 2-High | In Queue | http://jira04.switchlab.com/browse/URM-86 | Dharmaveeran/Natarajan | In-Progress | 2014-06-06
Old
1 | CRM | Bug | Without clicking on "Save as Prospective Customer" button, the details are recorded in CRM customers tab as in Prospect Status. | 2-High | Open | http://jira04.switchlab.com/browse/URM-276 | Dharmaveeran | Completed Solved and test in developement. | 31-May-2014
Expected: Ordering system should save order details only after the user clicks on "Save as Prospective customer" button and the same should reflect in CRM
2 | CRM | Bug | Right now same Cli can be allocated to any number of customers id. Whereas if a Cli has already been assigned to a particular customer then that Cli shouldn't be allocated to a different customer id, while doing that it should give an error message saying that the number is already allocated. | 2-High | Open | http://jira04.switchlab.com/browse/URM-290 | Natarajan | Solved and test in developement. Published in live | 31-May-2014
3 | CRM | Bug | While placing the order for the mobile shared plan, Deebu Duraisamy with his extension is showing as a default username and ext respectively in the CRM. | 2-High | Open | http://jira04.switchlab.com/browse/URM-291 | Natarajan | In-Progress | 31-May-2014
4 | CRM | Bug | Placed the order for mobile-shared plan with 24months but in the CRM end date is showing for 1 year instead of 2 years. | 2-High | Open | http://jira04.switchlab.com/browse/URM-292 | Dharmaveeran | Completed | 31-May-2014
5 | CRM | Bug | Order has been placed to add deskphone on 19.05.14 whereas in the CRM it is reflecting as active from 17.05.14. | 2-High | Open | http://jira04.switchlab.com/browse/URM-293 | Dharmaveeran | In-Progress | 31-May-2014
1 | My Account | Improvement | The alert message displayed is improper when the terms and conditions are not checked. |  | Open | http://jira04.switchlab.com/browse/UFM-457 | Magendiran | Completed
2 | My Account | Bug | Unable to add bundles from My Account |  | Open | http://jira04.switchlab.com/browse/UFM-473 | Magendiran | Completed
3 | My Account | Bug | Removal of bundles |  | Open | http://jira04.switchlab.com/browse/UFM-477 | Magendiran | Completed
4 | My Account | Bug | Correct number of Extensions aren't reflecting in Call History |  | Open | http://jira04.switchlab.com/browse/URM-295 | Magendiran | pending
1 | CRM | Issue | CRM project provision issue |  | Fixed |  | Ram | Fixed
1 | DB |  | Vectone-App-Mobile Report |  |  | Daily Job | Selveeswaran | Done
2 | DB |  | Chillitalk block |  |  |  | Selveeswaran | Done
3 | DB |  | Benney asked urgent update |  |  | ETalk -JIRA - Jira No : CS-124783 -benney asked urgent update | Selveeswaran | Completed
4 |  |  | Monthly Invoice |  |  | Monthly Invoice | Selveeswaran/Natarajan | In-progress

## Sheet2
CRM | Customer - Bug | Customer > product >mobile plans >select action >upgrade Action from CRM is not reflecting on MyAccount | 2-High | In Queue | http://jira04.switchlab.com/browse/URM-86

## 11-Jun-2014
Sl. No | System | Type | Description | Priority | Status | JIRA | Resource Name
1 | CRM | Bug | The Product Amount is inconsistent between CRM and MyAccount. MyAccount: Automated Operator cost is $10.00 CRM: Automated Operator is $15.00 | 2-High | Open | http://jira04.switchlab.com/browse/UFM-458
2 | CRM | Bug | Bundle isn’t showing with their respective numbers | 2-High | Open | http://jira04.switchlab.com/browse/URM-301
3 | CRM | Bug | Even though the Item is provisioned and dispatched the Sim extensions are not displayed for Individual sim plans in Products sub tab of Order tab. See attached screen shots. | Critical | Open | http://jira04.switchlab.com/browse/URM-303
4 | CRM | Bug | When trying to provision the mobile number, clicking on the provision button error message comes up but though the number gets provisioned When trying to dispatch the mobile number, though a error message comes up while clicking on the submit button of Royal mail reference the number gets dispatched. | 2-High | Open | http://jira04.switchlab.com/browse/URM-304
5 | CRM | Bug | On clicking product -> External number button shows “ 404 errors” This error was occurs in other tab also (occurs occasional) | 2-High | Open | http://jira04.switchlab.com/browse/URM-230 http://jira04.switchlab.com/browse/URM-265
6 | CRM | Bug | We placed renumber order for the cli:02070012965 and got the new cli:02030697773 yesterday. But it is not yet linked with the backened system though I have linked this cli with crm and my account. | 2-High | Open | http://jira04.switchlab.com/browse/URM-287
7 | CRM | Bug | In Query under customers tab we need to add one more search criteria “Mobile / LL no.” to search an existing customer. | 2-High | Open | http://jira04.switchlab.com/browse/URM-268
8 | CRM | Bug | Mentioning of a telephone number is mandatory while selecting Completed Line status | 2-High | Open | http://jira04.switchlab.com/browse/URM-294
9 | CRM | Bug | Customers are not getting email notification for some scenarios | 2-High | Open | http://jira04.switchlab.com/browse/URM-278
10 | CRM |  | Customer ->order click details In detail order items click cancel button the order was not cancelled | 2-High | Open | http://jira04.switchlab.com/browse/URM-225
Sl. No | System | Type | Description | Priority | Status | JIRA
1 | My Account | Bug | In Upgrade, GUI issue and Clear button not working | 2-High | Open | http://jira04.switchlab.com/browse/UFM-482
2 | My Account | Bug | In MyAccount, on clicking sub-menu - the menu is sliding and then expanding - which is causing bad user experience | 2-High | Open | http://jira04.switchlab.com/browse/UFM-483
3 | My Account | Bug | Extension numbers is not sorted in ascending order in "Features - User Extensions" page | 2-High | Open | http://jira04.switchlab.com/browse/UFM-484
4 | My Account | Bug | Improvements in Field Manager Functionality | 2-High | Open | http://jira04.switchlab.com/browse/UFM-485
5 | My Account | Bug | Number of Field Manager in My Account | 2-High | Open | http://jira04.switchlab.com/browse/UFM-486
6 | My Account | Bug | In Overview page of My Account the Deskphone calculation is incorrect. | 2-High | Open | http://jira04.switchlab.com/browse/UFM-487

## Sheet3
http://jira04.switchlab.com/browse/URM-244
http://jira04.switchlab.com/browse/URM-275
http://jira04.switchlab.com/browse/URM-277
http://jira04.switchlab.com/browse/URM-299
http://jira04.switchlab.com/browse/URM-309
5 | CRM | Bug | dispatched the Sim extensions are not displayed for Individual sim plans in Products sub tab of Order tab. See attached screen shots. | http://jira04.switchlab.com/browse/URM-303 | Data Issue , Please enter a new company and check | Not Fixed | a. SIM extensions are not displayed for Individual plan even item provisioned.
b. Server Error Showing while Provisioning for Shared plan. (refer attached Screenshot)

## Sheet4
DATE | JIRA_NO | Remark/Description | Resource Name | Status
6/16/2014 | Vectone App-mobile report prepared 16-06-2014 |  | Selveeswaran | CLOSED
6/16/2015 | Monthly Report -- updations |  | Selveeswaran | CLOSED
6/16/2016 | Monthly Report -- Stored procedure created and attached to Report - Get_Monthly_Invoice_prevcurrentmonthdate_Summary |  | Selveeswaran | CLOSED
6/16/2017 | Existing Customer Invoice Bill Creation |  | Selveeswaran | CLOSED
6/16/2018 | Chillitalk Block Accounts -product team |  | Selveeswaran | CLOSED
6/16/2019 | VASP-Reg.convert R-Kioski Invoice to XML format -Activation Team |  | Selveeswaran | CLOSED
6/16/2020 | Analyzed and fixed SIM provision SPS |  | Selveeswaran | CLOSED
6/16/2020 | http://jira04.switchlab.com/browse/URM-303 | Even though the Item is provisioned and dispatched the Sim extensions are not displayed for Individual sim plans in Products sub tab of Order tab. See attached screen shots. | Dharmaveeran | In-Progress
6/16/2020 | http://jira04.switchlab.com/browse/URM-303 | Even though the Item is provisioned and dispatched the Sim extensions are not displayed for Individual sim plans in Products sub tab of Order tab. See attached screen shots. | Natarajan | In-Progress
6/16/2020 | User Management Use-case | System Study | Natarajan | In-Progress
6/16/2020 | Monthly Invoice |  | Natarajan | Testing
6/16/2020 | http://jira04.switchlab.com/browse/VBP-273 | Shared- SIM type should not replace with the existing and accord to SIM type its display separately Individual - Remove Option not working properly | Ram | CLOSED
6/16/2020 | http://jira04.switchlab.com/browse/VBP-269 | Monthly cost calculation is wrong and In CRM, Ordered items not reflected. I didn't ordered Switchboard but its displays in CRM Order Items. | Ram | CLOSED
6/16/2020 | http://jira04.switchlab.com/browse/UFM-483 | In MyAccount, on clicking sub-menu - the menu is sliding and then expanding - which is causing bad user experience | Magendiran | In-Progress
6/16/2020 | http://jira04.switchlab.com/browse/UFM-488 | Adding bundles | Magendiran | In-Progress

## Sheet5
DATE | JIRA_NO | Remark/Description | Resource Name | Status
6/17/2020 | http://jira04.switchlab.com/browse/URM-303 | Even though the Item is provisioned and dispatched the Sim extensions are not displayed for Individual sim plans in Products sub tab of Order tab. See attached screen shots. | Dharmaveeran | In-Progress 80 % Data fix done,We need to check
6/17/2020 | http://jira04.switchlab.com/browse/URM-303 | Even though the Item is provisioned and dispatched the Sim extensions are not displayed for Individual sim plans in Products sub tab of Order tab. See attached screen shots. | Selveeswaran | In-Progress 80 % Data fix done,We need to check
6/17/2020 | User Management Use-case | System Study | Natarajan | Completed Table Design Done
6/17/2020 | http://jira04.switchlab.com/browse/URM-86 |  | Natarajan | System Design
6/17/2020 | http://jira04.switchlab.com/browse/URM-86 |  | Dharmaveeran | GUI Changes - Inprogress
6/17/2020 | http://jira04.switchlab.com/browse/URM-86 |  | Selveeswaran | DB Changes Inprogress
6/17/2020 | http://jira04.switchlab.com/browse/VBP-273 | Shared- SIM type should not replace with the existing and accord to SIM type its display separately Individual - Remove Option not working properly | Ram | CLOSED
6/17/2020
6/17/2020 | http://jira04.switchlab.com/browse/UFM-482 | In Upgrade, GUI issue and Clear button not working | Magendiran | Fixed
6/17/2020 | http://jira04.switchlab.com/browse/UFM-483 | In MyAccount, on clicking sub-menu - the menu is sliding and then expanding - which is causing bad user experience | Magendiran | Fixed
6/17/2020 | http://jira04.switchlab.com/browse/UFM-484 | Extension numbers is not sorted in ascending order in "Features - User Extensions" page | Magendiran | Fixed
6/17/2020 | http://jira04.switchlab.com/browse/UFM-485 | Improvements in Field Manager Functionality | Magendiran | Fixed
6/17/2020 | http://jira04.switchlab.com/browse/UFM-486 | Number of Field Manager in My Account | Magendiran | Fixed
6/17/2020 | http://jira04.switchlab.com/browse/UFM-487 | Calculation of Deskphone in Overview page | Magendiran | Fixed
6/17/2020 | http://jira04.switchlab.com/browse/UFM-488 | Adding bundles | Magendiran | In process

## Sheet6
SrlNo | Remark/Description | Status | JIRA_NO | Resource Name
1 | Search customer by its company name Select the company name Search company in customer query | Open | http://jira04.switchlab.com/browse/URM-244 | Dharmaveeran
2 | In Customers tab, Company details are not recorded for Prospect customers. And While updating details in Company, Billing, Admin and Dispatch details the alert message was showing wrongly. | Open | http://jira04.switchlab.com/browse/URM-275 | Dharmaveeran
3
|  | Completed | Vectone App-mobile report prepared 17-06-2014 | Selveeswaran
4 |  | Completed | Registration Billing issue Resolved -Ordering | Selveeswaran
|  | NOT FIXED | 303 Issue Analzed-Ordering -SQL Server doesn't officially support loopback server scenario | Selveeswaran
5 |  | Completed | http://10.30.2.18/browse/CS-125693 | Selveeswaran
|  | Completed | http://10.30.2.18/browse/CS-125782 | Selveeswaran
6
| User Management - Super User Flow | Completed |  | Natarajan
7 | User Management - Super User Creation | Inprogress |  | Natarajan
| GUI Desing | Inprogress |  | Magendiran